## weight
Weight (lb) | Description | Empty/Full | Type | Location (% Front) | Front Weight | Rear Weight |  | Limits (lb) | Actual (lb) | Percentage of Limit | Available
250 | passanger |  | base | 50% | 125 | 125 | Total | 12300 | 8795.6606 | 71.51% | 3504.3394
180 | me |  | base | 100% | 180 | 0 | Front Axle | 4601 | 4107.5545 | 89.28% | 493.4455 | NOTE: Front Axle + Rear Axle Limits DO NOT add up to Total
19.2 | Aux Fuel Tank | full | HVAC | 40% | 7.68 | 11.52 | Rear Axle | 8600 | 4688.1061 | 54.51% | 3911.8939
13.2 | mexico blanket |  | personal item | 50% | 6.6 | 6.6
11.8 | extension cord |  | electrical | 50% | 5.9 | 5.9 |  | Tare (lb)
7.8 | cooler | empty | food | 80% | 6.24 | 1.56 | Total | 8024.2744
117 | cork underlayment |  | envelope | 30% | 35.1 | 81.9 | Front Axle | 3686.5223
167.7256 | cork flooring |  | envelope | 30% | 50.3177 | 117.4079 | Rear Axle | 4337.7521
4.6606 | spare cork flooring tile |  | envelope | 90% | 4.1945 | 0.46606 |  | 8024.2744
[7 empty] | bus | 8560 |  | flooring | 179 | underlayment | 117
CAT SCALE WEIGHT:
5010KG | [6 empty] | fuel | 19.2 |  | spare tile |  | scraps
[7 empty] | me | 180 |  | scraps | 6.6139 | leftover
[7 empty] | extension | 11.8
[7 empty] | garbage | 1.2
[7 empty] | cooler | 7.8
[7 empty] | backpack | 13.2
[7 empty] | blanket | 4.2
[7 empty] | cable + lugs | 5
[7 empty] | First aid + fire extinguisher + hand san | 8.6
[7 empty] | flooring | 167.7256 |  |  |  |  | 117
[7 empty] | underlayment | 117
8024.2744

## trash
Weight Log |  |  | Garbage | Recycling | Water Pollutants | Not Accounted | Materials Leftover
description | weight (lbs) | tag | description | description | description | description | description | weight (lbs)
plastic | 36 | gutting | paper towel | cardboard | windex | wheelchair anchors and straps | cork flooring | 6.6139
fiberglass | 23.6 | gutting | 2 wiper blades | plastic | wd40 | wheelchair anchor plates
fabrics/foams/polystyrene | 20.8 | gutting | razor blades | packaging | acetone | wheelchair lift
linoleum | 124.2 | gutting | broken glass |  | goo gone
plywood | 206.4 | gutting | tape |  | dawn dish soap
steel | 72.8 | gutting | silicone |  | plastic car trim spray
aluminum | 90 | gutting | box air filters |  | tire shine spray
5 tires |  |  | respirator filters |  | green stuff organic cleaner
garbage | 52.8 |  | n95 masks |  | interior car cleaner
recycling | 18.4 |  | cable shroud |  | interior car polish
aluminum | 0.5 | floor trim | plastic bits |  | exterior car polish/wax
cardboard + plastic mix | 2.8 |  | stickers, vinyl |  | barkeepers friend
cardboard packaging | 12.6 |  | garbage found in bus on purchase |  | vinegar bath with rust + paint from cleaning steel
foam packaging | 1.4 |  | buffing pads |  | washing the paint brush down the sink
garbage | 11.4 | parents house | rusty metal bits |  | grinding metal/paint/glue outside
wood waste | 18 | parents house | particulates/dust - rust, wood, paint, metal, insulation |  | scraping caulking outside
recycling | 8.2 | parents house | sawdust |  | engine oil
metal | 1 | parents house | paint |  | engine coolant
paper/cardboard | 5 | on the road | nitrile gloves |  | diesel
cans | 0.4 | on the road | angle grinder wheels
plastic | 1.6 | on the road | paint trays
garbage | 7 | on the road | paint rolls
recycling | 2 | on the road | diesel oil covered paper towel, gloves
batteries | 0.5 | on the road
recycling | 1.2 | on the road
propane tanks | 1 | on the road
trash | 6.2 | on the road
plastic bags | 1 | on the road
paper/cardboard | 6.2 | on the road
recycling | 5 | on the road
trash | 9.6 | on the road
metal | 1 | on the road

## costs
description | quantity | amount | category | vendor | date | url | action
wipers |  | 56.48 | vehicle | canadian tire | 2021-07-15
3M 2097 P100 Particulate Filter with Organic Vapor Relief | 2 | 33.11 | consumables | amazon | 2021-08-02 | https://www.amazon.ca/gp/product/B079X5C3QP
3M Multi Gas/Vapor Cartridge/Filter 60926, P100 Respiratory Protection | 1 | 41.91 | consumables | amazon | 2021-08-02 | https://www.amazon.ca/gp/product/B009POHLRC
3M Peltor Optime 101 Over-The-Head Earmuffs H7A | 1 | 39.08 | tool | amazon | 2021-08-11 | https://www.amazon.ca/gp/product/B000J05EZW
Bosch CO21B 21 Pc. Cobalt M42 Drill Bit Set | 1 | 91.96 | tool | amazon | 2021-08-11 | https://www.amazon.ca/gp/product/B07Q64LTFB
40 grit sanding wheel | 1 | 16.7 | consumables | canadian tire | 2021-08-14
3M Particulate Filter 2097 | 1 | 36.75 | consumables | amazon | 2021-09-03 | https://www.amazon.ca/gp/product/B07PY3X2P8
Paint Stripper, 5Pcs 100mm Poly Strip Wheel Disc Paint Rust Removal Tool for Angel Grinders | 5 | 23 | consumables | amazon | 2021-09-03 | https://www.amazon.ca/gp/product/B0989Q3CVM
North by Honeywell Silver Shield 14.5" Chemical-Resistant Pv/Evoh Gloves, 2.7 Mil, Size 11 (RWS-57038) | 1 | 22.78 | consumables | amazon | 2021-09-06 | https://www.amazon.ca/gp/product/B0719S4PJ2
Wooster Brush Q3108-2 Softip Paintbrush, 2-Inch | 2 | 9.54 | consumables | amazon | 2021-09-06 | https://www.amazon.ca/gp/product/B000ZZUKY6
Scotch-Brite Clean and Strip XT Pro Disc – Rust and Paint Stripping Disc – 4.5” diam. x 5/8-11 Quick Change Thread – Extra Coarse Silicon Carbide – Pack of 1 | 1 | 31.96 | consumables | amazon | 2021-09-16 | https://www.amazon.ca/gp/product/B07L1CXBRZ
extension cord |  | 97.18 | tool | canadian tire | 2021-09-22
5PCS 100mm 60# Poly Strip Wheel Disc Abrasive Angel Grinders Clean Tool for Rust/Paint/Flaking Materials Removal - Purple&Gold | 15 | 136.59 | consumables | amazon | 2021-09-23 | https://www.amazon.ca/gp/product/B07K19L38B
Vastar Universal Smartphone Tripod Adapter Cell Phone Holder Mount Adapter, Fits iPhone, Samsung, and All Phones, Rotates Vertical and Horizontal, Adjustable Clamp | 1 | 18.39 | materials | amazon | 2021-09-23 | https://www.amazon.ca/gp/product/B01L3B5PBI
SafeGuard Disposable Nitrile Gloves. 5 mil Single-use XLarge Black Powder-free Latex-free Ambidextrous Disposable Nitrile Gloves | 50 | 49.42 | consumables | amazon | 2021-09-29 | https://www.amazon.ca/gp/product/B00RTZZCSO
SmallRig Clamp Mount with Ball Head Mount Hot Shoe Adapter and Cool Clamp - 1124 | 1 | 18.89 | tool | amazon | 2021-09-29 | https://www.amazon.ca/gp/product/B00DOMVJ92
Tseipoaoi 12V 5000W Parking Heater Diesel Air Heater 10L Tank With LCD Monitor Control Remote Control Parking Fan Heater Defroster for Car/Motor-Home/Boat/Bus(Suitable for high altitude areas | 1 | 265.64 | HVAC | amazon | 2021-10-01 | https://www.amazon.ca/gp/product/B07VT24CLK
silicone |  | 10.4 | materials | canadian tire | 2021-10-08
Self Adhesive Cork Squares, MOTASOM 4 x 4 Inch Strong Cork Adhesive Sheets, Reusable Cork Board Cork Backing Sheets, Mini Wall Cork Tiles Mat for Coasters and DIY Crafts (120Pcs) | 120 | 39.89 | materials | amazon | 2021-10-14 | https://www.amazon.ca/gp/product/B087841MVP
mr. buddy propane heater | 1 | 172.45 | HVAC | canadian tire | 2021-10-20
Blueair Blue Pure 411 Auto Small Room Air Purifier with Auto Mode for Allergies, Pollen, Dust, Smoke, Pet Dander, Viruses and Bacteria with HEPASilent Technology and Washable Pre-Filter | 1 | 229.99 | HVAC | amazon | 2021-10-22 | https://www.amazon.ca/gp/product/B08FCX8Z52
First Alert PRC710A-6 Slim Series Photoelectric Smoke & Carbon Monoxide Detector | 1 | 57.47 | safety | amazon | 2021-10-22 | https://www.amazon.ca/gp/product/B0813DQJHV
LED Flashlight USB Rechargeable Flashlight High Power COB Workshop Flashlights (Including 18650 Battery) Small Lightweight Walking Powerful Tactical Camping Flashlights for Outdoor Hiking Sports(2 Pack | 2 | 34.64 | tool | amazon | 2021-10-22 | https://www.amazon.ca/gp/product/B083W9SKND
MTI 40-442-P-WT Industris 12 Volt Flush Mount White Propane Gas Detector | 1 | 83.61 | safety | amazon | 2021-10-22 | https://www.amazon.ca/gp/product/B000AMBHGE
OTYTY 2 COB 30W 1500LM LED Work Light, Rechargeable Portable Waterproof LED Flood Lights for Outdoor Camping Hiking Emergency Car Repairing and Job Site Lighting (2 Pack) | 2 | 49.94 | tool | amazon | 2021-10-22 | https://www.amazon.ca/gp/product/B07GCBHMZ8
Supa Ant Eco-Friendly (1500֯F) Fire Blanket, High Visibility CE Certified Emergency Fire Blanket for Home, Kitchen, Car, Van, RV, Office, Reusable (39.3x39.3 in) (2 Fire Blankets + 2Hooks) | 2 | 26.45 | safety | amazon | 2021-10-22 | https://www.amazon.ca/gp/product/B08LDGTG88
Victron Energy SmartSollar MPPT 150/60-TR | 1 | 763.485 | electrical | volts energies | 2021-10-22
Victron Energy VE.Bus Smart Dongle | 1 | 110.6185 | electrical | volts energies | 2021-10-22
Victron Energy Orion-Tr 12/12-30A DC-DC Charger | 1 | 370.3 | electrical | volts energies | 2021-10-22
Victron Energy MultiPlus 12/3000/120-50 Inverter/Charger | 1 | 1816.724 | electrical | volts energies | 2021-10-22
Victron Energy Temp Sensor | 1 | 34.868 | electrical | volts energies | 2021-10-22
Victron Energy 500A Smart Shunt | 1 | 182.85 | electrical | volts energies | 2021-10-22
Peimar SM400M BF Solar Panel 400W | 4 | 1379.954 | electrical | volts energies | 2021-10-22
Uxcell US-SA-AJD-144156 50ft 0.1mm AWG38 Nichrome Resistance Heating Coils Resistor Wire | 1 | 12.64 | tool | amazon | 2021-10-23 | https://www.amazon.ca/gp/product/B019MNNRN2
XINGYHENG 400W DC-DC High Power Boost Converter Adjustable Step Up Constant Voltage Constant Current Power Supply Module LED Drive Notebook Battery Charging with Short Circuit Protection | 1 | 16.79 | tool | amazon | 2021-10-23 | https://www.amazon.ca/gp/product/B08XNM22YV
Digital Clamp Meter DC AMP Meter AP-570C-APP 4000 Counts Bluetooth Clamp Meter with Temp Testing, Measures Current, Voltage, Resistance, Capacitance, Temperature, Frequency, Duty Cycle, Clamp on Ampmeter | 1 | 56.69 | tool | amazon | 2021-10-24 | https://www.amazon.ca/gp/product/B08BZCHSJR
propane cannister | 1 | 10.3385 | consumables | canadian tire | 2021-10-25
DEWALT DCK240C2 20V MAX Cordless Drill & Impact Driver Combo Kit, 1.3Ah | 1 | 229.9885 | tool | canadian tire | 2021-10-25 | https://www.canadiantire.ca/en/pdp/dewalt-dck240c2-20v-max-cordless-drill-impact-driver-combo-kit-1-3ah-0542320p.html
Electrical Breaker Box Plastic Transparent Cover Power Distribution Protection Box for 3-4 Ways Circuit Breaker Indoor on The Wall | 1 | 19.94 | electrical | amazon | 2021-10-27 |  | returned
Leviton 80301-SE 1-Gang Decora Plus Wallplate Screwless Snap-On Mount (Black) | 1 | 9.76 | electrical | amazon | 2021-10-27 |  | returned
Lincoln Electric KH538 Lug/Cable Crimping Tool | 1 | 27.9 | tool | amazon | 2021-10-27 | https://www.amazon.ca/gp/product/B00F0SLLFA | returned
MGI SpeedWare Power Junction Posts, Stainless Steel Studs Red + Black (5/16") | 1 | 29.45 | electrical | amazon | 2021-10-27 |  | returned
NOCO GCP1 15 Amp 125V AC Port Plug Power Inlet with 16-Inch Integrated Extension Cord | 2 | 57.46 | electrical | amazon | 2021-10-27
Q230 30-Amp Double Pole Type QP Circuit Breaker | 1 | 22.05 | electrical | amazon | 2021-10-27 | https://www.amazon.ca/gp/product/B00002N5HJ | returned
T Tocas 300A Bus Bars Heavy Duty Module Design Power Distribution Block Busbar Box with 4X M10(3/8") Terminal Studs | 2 | 104.98 | electrical | amazon | 2021-10-27 |  | returned
250pcs Heat Shrink Wire Connectors, Sopoby Marine Electrical Terminals Kit, Waterproof Automotive Ring Set with Case | 1 | 30.44 | electrical | amazon | 2021-10-27
4 Pack 120mm Computer Fan Filter Grills with Screws, Ultra Fine Aluminum Mesh, Black Color | 4 | 15.74 | HVAC | amazon | 2021-10-27
Blue Sea Systems 5005, 35 to 300 Amp Anl Fuse Block with Insulating Cover | 6 | 237.3 | electrical | amazon | 2021-10-27 | https://www.amazon.ca/Blue-Sea-Systems-5005-Insulating/dp/B000K2K7TW
Blue Sea Systems 5127, 150 Amp Anl Fuse | 1 | 32.18 | electrical | amazon | 2021-10-27
Blue Sea Systems 5131, 250 Amp Anl Fuse | 1 | 80.46 | electrical | amazon | 2021-10-27 | https://www.amazon.ca/gp/product/B000K2K6Q6
Blue Sea Systems ANL Fuse 50 AMP | 1 | 34.48 | electrical | amazon | 2021-10-27 | https://www.amazon.ca/gp/product/B000THQSB4
Blue Sea Systems ANL Fuse 60 AMP | 2 | 64.36 | electrical | amazon | 2021-10-27 | https://www.amazon.ca/gp/product/B000THT1SG
Blue Sea Systems m-Series Battery Switch | 1 | 76.33 | electrical | amazon | 2021-10-27 | https://www.amazon.ca/gp/product/B00445KFZ2
BlueFire Upgraded 12 Way Blade Fuse Box Fuse Holder Standard Circuit Fuse Holder Box Block with LED Indicator, Fuses & Protection Cover for Car Boat Marine Truck Vehicle SUV Yacht RV | 1 | 37.79 | electrical | amazon | 2021-10-27
Leviton GFNT1-E Self-Test SmartlockPro Slim GFCI Non-Tamper-Resistant Receptacle with LED Indicator, 15 Amp, Black | 1 | 33.83 | electrical | amazon | 2021-10-27
Noctua NF-S12B redux-700, Ultra Quiet Silent Fan, 3-Pin, 700 RPM (120mm, Grey) | 2 | 38.66 | electrical | amazon | 2021-10-27
PowMr 15A M-C-4 Waterproof in-Line Holder w/Fuse, Black | 2 | 35.46 | electrical | amazon | 2021-10-27
RockDIG 50 pcs AWG 8/6/4/2 Heavy Duty Bare Copper Lugs, Closed End Tubular Ring Terminals, Battery Electrical Cable Wire Connectors Assortment Kit(with 50 pcs Heat Shrink Tubings) | 1 | 45.14 | electrical | amazon | 2021-10-27
Titan 11477 Ratcheting Wire Terminal Crimper | 1 | 24.14 | tool | amazon | 2021-10-27 | https://www.amazon.ca/gp/product/B0069TRKJ0
Extech 480172 AC Line Splitter | 1 | 25.59 | tool | amazon | 2021-10-28 | https://www.amazon.ca/gp/product/B0000YHN9W
IP68 Waterproof Solar Cable Entry Gland | 2 | 27.29 | electrical | amazon | 2021-10-28 | https://www.amazon.ca/gp/product/B07WL7D9V6
Mssoomm Copper Flat Bar 5mm x 50mm x 1000mm, C110 Copper Bus Bar 99% Copper T2 Cu Metal | 1 | 152.61 | electrical | amazon | 2021-10-28
Ruikarhop MC4 Connectors Y Branch 1 to 2 Parallel Adapter Cable Wire Plug,MC4 Assembly Tool and 5 Pair MC4 Male/Female Solar Panel Cable Connectors | 2 | 21.89 | electrical | amazon | 2021-10-28 | https://www.amazon.ca/gp/product/B07S8VZZ2D
2/0 lug nuts | 3 | 18.5955 | electrical | batteries dixon | 2021-10-29
CAT Scale | 1 | 22 | other | Groupe Re Inc. | 2021-10-29
4/0 AWG Cable 2 meters | 1 | 69 | electrical | batteries dixon | 2021-10-29
4/0 AWG Cable Lugs, 5/16" | 11 | 68.1835 | electrical | batteries dixon | 2021-10-29
cardboard moving boxes | 8 | 13.8 | consumables | rona | 2021-11-01
2p DC 250V Miniature Circuit Breaker | 1 | 27.12 | electrical | amazon | 2021-11-02 | https://www.amazon.ca/gp/product/B07HG5TYPT
Hfs (R) 16 Ton Hydraulic Wire Terminal Crimper Battery Cable Lug Crimping Tool W/Dies | 1 | 97.72 | tool | amazon | 2021-11-02 | https://www.amazon.ca/gp/product/B0761HR9V5
how to build with gridbeam E-book |  | 21.98 |  | new society publishing | 2021-11-04
6 64L transparent storage bins (19.99+tax), 3 64L black bins (~$10) | 9 | 172.1895 | tool | home depot | 2021-11-06
folding table | 1 | 67.827 | tool | home depot | 2021-11-06
1.5" x 1.5" x 6' pine | 1 | 9.039 | materials | home depot | 2021-11-06
1/4" bolts | 10 | 8.74 | materials | home depot | 2021-11-06
sand paper 9 x 11 sheets various |  | 2.254 | consumables | home depot | 2021-11-06
cooking pot, cork place mat |  | 14.5 | kitchen | LIBRARIE RENAISSANCE thrift | 2021-11-07
1/4 threaded rod 36", 8ft aluminum 1"x1" L bar, 3M electrical tape |  | 91.37 |  | home depot | 2021-11-08 |  | breakdown
connector bolts, weld nuts, t nuts, loctite, dowel nuts, brad point drill bits, lock nuts, routing eye bolt, u bolt, vibration damping sandwitch mount, 1/2 steel washers) |  | 384.35 | materials | mcmaster-carr | 2021-11-08 |  | breakdown
clear silicone tube | 1 | 10.6835 | materials | canadian tire | 2021-11-08
white ash raw lumber 8/4 10' x 7" | 6 | 361.6 | materials | langevin forest | 2021-11-08
mastercraft clamp set | 14 | 26.4385 | tool | canadian tire | 2021-11-17 | https://www.canadiantire.ca/en/pdp/mastercraft-spring-clamp-set-14-pc-0572724p.html
MAXIMUM Mixed Hex Bit Carabiner Clip Set, 10-pc | 10 | 11.4885 | tool | canadian tire | 2021-11-17 | https://www.canadiantire.ca/en/pdp/maximum-mixed-hex-bit-carabiner-clip-set-10-pc-0543782p.html
mastercraft C-type clamp | 3 | 20.6655 | tool | canadian tire | 2021-11-17 | https://www.canadiantire.ca/en/pdp/mastercraft-c-type-clamp-0572610p.html
aluminum duct 4" x 8' | 2 | 32.062 | materials | home depot | 2021-11-25
GPS 2" insulation 4x8 | 1 | 42.2165 | materials | home depot | 2021-11-25
GPS 1" insulation 4x8 | 2 | 51.934 | materials | home depot | 2021-11-25
3" to 4" duct converter | 2 | 13.984 | materials | home depot | 2021-11-25
4" aluminum duct connector | 2 | 8.326 | materials | home depot | 2021-11-25
4" hose clamps | 6 | 14.49 | materials | home depot | 2021-11-25
20L bucket | 1 | 4.3355 | tool | home depot | 2021-11-25
20L bucket lid | 1 | 3.4155 | tool | home depot | 2021-11-25
rubber steps | 2 | 11.454 | materials | home depot | 2021-11-25
mattress bag | 1 | 15.6745 | tool | home depot | 2021-11-25
expanding foam | 1 | 15.18 | materials | home depot | 2021-11-25
3/8" baltic birtch 29 3/4" x 60" | 5 | 177.9625 | materials | langevin forest | 2021-11-25
5/16" wood dowel 48" | 3 | 3.4155 | materials | langevin forest | 2021-11-25
1L ligna biosupra natural oil | 1 | 103.4425 | materials | langevin forest | 2021-11-25
sand paper 600 grit | 1 | 2.2425 | consumables | langevin forest | 2021-11-25
sand paper 1200 grit | 1 | 1.8285 | consumables | langevin forest | 2021-11-25
sand paper 2000 grit | 1 | 1.8285 | consumables | langevin forest | 2021-11-25
scouring pad | 2 | 4.807 | consumables | langevin forest | 2021-11-25
incra T precision ruler | 1 | 40.1925 | tool | langevin forest | 2021-11-25
4" air duct closing door | 2 | 12.535 | materials | langevin forest | 2021-11-25
sewing supplies - needles and thread |  | 13.8 | materials | J & L Coupons | 2021-11-27
5L 0W40 Shell Rotella T6 Engine Oil | 2 | 133.377 | consumables | canadian tire | 2021-12-02
Diesel Kleen Flo Fuel Conditioner 1L | 1 | 9.1885 | consumables | canadian tire | 2021-12-02
Tuck Tape | 1 | 14.9385 | materials | canadian tire | 2021-12-02
Mass Air Flow Sensor Cleaner | 1 | 11.4885 | consumables | canadian tire | 2021-12-02
64L black bins | 3 | 41.2965 | tool | home depot | 2021-12-04
milk crate | 1 | 11.3505 | tool | home depot | 2021-12-04
6.5-Amp 1.25 HP Compact Router with Fixed Base, 5 Trim Router Bits, Variable Speed, Edge Guide, Roller Guide and Dust Hood, Avid Power MW104 | 1 | 101.69 | cnc | amazon | 2021-12-07
Usongshine 5pcs 17HS4401 High Torque Bipolar Stepper Motor Nema 17, 0.46Nm Low Noise 42 DC Step Motor Kit, 1.8°2-Phrase Universal Electric Motor DC Motor for 3D Printer Laser Engraving | 5 | 48.58 | cnc | amazon | 2021-12-07
LLPT Hook and Loop Tape Roll 1 Inch x 33 Feet Nylon Fabric without Adhesive Strong Hook Loop Strip for Sewing Indoor Outdoor on DIY Cloth Shoe Curtain Bag Sport Gears (NHTW33) | 2 | 38.4 | materials | amazon | 2021-12-07
20 Pack608-2RS Ball Bearings – Bearing Steel and Double Rubber Sealed Miniature Deep Groove Ball Bearings for Skateboards, Inline Skates, Scooters (8mm x 22mm x 7mm) | 20 | 22.59 | cnc | amazon | 2021-12-07
KeeYees GT2 Timing Belt Pulley 16 Teeth 5mm Bore with Allen Wrench for 6mm Width 3D Printer Belt | 6 | 11.29 | cnc | amazon | 2021-12-07
Eiechip CNC 3D Printer Kit for Arduino Mega 2560 R3 + RAMPS 1.4 Controller + LCD 2004 + 6X Limit Switch Endstop + 5 A4988 Stepper Driver 3D Printer Interface & Driver Modules | 1 | 58.75 | cnc | amazon | 2021-12-07
Naler Cotton Tape, Bias Tape for Sewing Bunting Tape Twill Webbing Tape Apron DIY Craft Dressmaking Sewing Home Decor (15m x 2.5cm, White) | 1 | 19.2 | materials | amazon | 2021-12-07
CNC power supply | 1 | 33.45 | cnc | amazon | 2021-12-08
GE Silicone White | 1 | 8.9355 | materials | home depot | 2021-12-08
Sanding Disks Various Size | 50 | 42.2395 | consumables | home depot | 2021-12-08
GPS 1" insulation 4x8 | 3 | 50.025 | materials | home depot | 2021-12-08
1/8 4 x 8 Hardboard | 3 | 45.678 | materials | home depot | 2021-12-08
Tuck Tape | 2 | 23.87 | materials | home depot | 2021-12-09
Hot Rolled Angle 1.500 x 1.500 x 0.125 x 96 | 1 | 22.6 | materials | metal supermarkets | 2021-12-09
Car Seat - Bucket with manual rail and built in seat belt | 1 | 41.57 | materials | kenny u-pull | 2021-12-09
Steel WaterJet cutting | 1 | 160 | cnc | RMC Waterjet Services | 2021-12-09
EverBilt Industrial 4.5" Door Hinges | 6 | 157.14 | materials | home depot | 2021-12-12
10' Superstrut Channel | 1 | 65.48 | materials | home depot | 2021-12-12
Hockey Pucks | 14 | 32.24 | materials | sportchek | 2021-12-12
Twill tape 3" | 5 | 45.8275 | materials | walmart | 2021-12-13
FJÄLLARNIKA Duvet | 1 | 100.57 | household | ikea | 2021-12-27
VILDKORN Pillow | 1 | 13.5487 | household | ikea | 2021-12-27
BERGPALM duvet cover and pillowcase(s) | 1 | 33.8887 | household | ikea | 2021-12-27
NÄVLINGE LED wall/clamp spotlight | 1 | 22.5887 | household | ikea | 2021-12-27
SÖMNTUTA fitted sheet | 1 | 33.8887 | household | ikea | 2021-12-27
Laundry Hamper | 1 | 4.52 | household | dolarama | 2021-12-31
Baking soda | 1 | 1.25 | household | dolarama | 2021-12-31
Dishpan | 1 | 2.825 | household | dolarama | 2021-12-31
small plastic box | 3 | 3.39 | household | dolarama | 2021-12-31
container | 1 | 2.825 | household | dolarama | 2021-12-31
dish scrubber with handle | 1 | 1.4125 | household | dolarama | 2021-12-31
ziplock bags small |  | 3.39 | household | dolarama | 2021-12-31
ziplock bags medium |  | 4.52 | household | dolarama | 2021-12-31
shower curtain | 1 | 4.52 | household | dolarama | 2021-12-31
Washer Fluid 1 Gal | 2 | 15.7974 | vehicle | gas station | 2021-12-31
Dustpan | 1 | 5.6161 | household | walmart | 2021-12-31
20L Diesel Jerry Can | 1 | 25.7488 | vehicle | canadian tire | 2022-01-01
Dessicant | 1 | 14.5488 | HVAC | canadian tire | 2022-01-01
RD34/78 Optima Red Top AGM Battery 800CCA | 2 | 743.6576 | vehicle | canadian tire | 2022-01-01
Reflex Allseason Washer Fluid 1 Gal | 2 | 8.848 | vehicle | canadian tire | 2022-01-01
rent | 4 | 1052.5 | makerspace | LESPACEMAKER |  |  | add up recent rent
sensors |  | 369.97 | smart | adafruit |  |  | breakdown
painting supplies (tremclad paint, tray liner, brush, roller) |  | 80.07 | materials | peintures cite |  |  | breakdown
box of stainless 3/8-16 nuts |  | 18.62 | materials | home depot
floor bolt nuts | 20 | 23.73 | materials | mcmaster-carr
rubber seal (ft) | 1 | 75.69 | materials | mcmaster-carr
floor bolt washers - Grade 9 Steel Washer Zinc Yellow-Chromate Plated, 1/2" Screw Size, 1.092" OD |  | 25.52 | materials | mcmaster-carr
floor bolts - High-Strength Grade 8 Steel Hex Head Screw Zinc-Aluminum Coated, 1/2"-13 Thread Size, 4-3/4" Long | 20 | 68.87 | materials | mcmaster-carr
aerogel insulation |  | 1679.96 | materials | aerogel
paid brother to remove remaining vinyl |  | 20 | other | other
20x20 3M Furnace Air Filter rated 1000 | 1 | 20.89 | consumables | rona
incomplete socket set |  | 5.8 | tool | eco depot
large drill bit |  | 0.4 | tool | eco depot
roll of insulation |  | 5 | materials | eco depot
bus + dealer registration fee |  | 6896 | vehicle | first student canada
OEM Girardin window latches | 4 | 48.09 | materials | girardin
vinegar |  | 4 | consumables | other
3/8-16x1" galvanized hex bolts | 18 | 11.39 | materials | home depot
20" box fan | 1 | 20 | tool | kijiji
3M 6900 respirator | 1 | 120 | tool | kijiji
cork flooring (sqft) | 109 | 220 | materials | kijiji
cork underlayment 80x3ftx2ft | 480 | 140 | materials | kijiji
lithium battery | 1 | 800 | electrical | kijiji
mixed lot of fasteners |  | 5 | materials | kijiji
sears 5 ton bottle jack | 1 | 10 | tool | kijiji
key fob deposit |  | 10 | makerspace | LESPACEMAKER
membership | 4 | 300 | makerspace | LESPACEMAKER
metal shop and mig welding training |  | 91.98 | makerspace | LESPACEMAKER
project space rental (days) | 6 | 24 | makerspace | LESPACEMAKER
rent deposit |  | 197.5 | makerspace | LESPACEMAKER
wood shop consumables fee |  | 20 | makerspace | LESPACEMAKER
wood shop planer, jointer and router training |  | 57.49 | makerspace | LESPACEMAKER
wood shop training |  | 57.49 | makerspace | LESPACEMAKER
1" hook and loop tape (ft) | 50 | 94.36 | materials | mcmaster-carr
20x20 Furnace Filter rated merv 9 | 2 | 26.63 | consumables | mcmaster-carr
23 month MTO license plate sticker |  | 230 | vehicle | other
wheelchair lift |  | -400 | vehicle | other
circa 1850 stripper | 1 | 20.48 | materials | peintures cite
corroseal 1 gal | 1 | 101.2 | materials | peintures cite
paint roller | 1 | 3.45 | consumables | peintures cite
paint tray | 1 | 6.9 | tool | peintures cite
paint tray liner | 1 | 4.95 | consumables | peintures cite
rubber stripping gloves | 1 | 6.84 | consumables | peintures cite
diesel heater fuel line priming syringe | 1 | 1 | HVAC | pharma prix
1/2" socket adapter | 1 | 6.31 | tool | princess auto
20 ton bottle jacks | 2 | 114.98 | tool | princess auto
40/40/60/80 sanding wheels | 4 | 33.53 | consumables | princess auto
cutting wheel | 3 | 10.9 | consumables | princess auto
cutting wheel | 1 | 6.89 | consumables | princess auto
tuck tape | 1 | 11.5 | materials | princess auto
wheel chocks | 2 | 13.78 | tool | princess auto
air filter | 1 | 58.99 | vehicle | rock auto
fuel filter | 1 | 119.72 | vehicle | rock auto
oil filters | 5 | 62.96 | vehicle | rock auto
5 mil nitrile gloves | 50 | 36.79 | consumables | rona
abbrasion resistant work gloves | 1 | 12.06 | consumables | rona
knee pads | 1 | 12.64 | tool | rona
work gloves |  | 8.61 | consumables | rona
work gloves |  | 5.74 | consumables | rona
safety inspection |  | 183.06 | vehicle | tool box auto shop
rear tire road force balancing | 4 | 120 | vehicle
tires + balancing | 6 | 1850.94 | vehicle
First Aid Kit | 1 | 28.2387 | household | pharmasave | 2021-12-30
Isopropyl Alcohol 99% | 1 | 7.8987 | household | pharmasave | 2021-12-30
Diesel 911 | 1 | 33.8887 | vehicle | gas station | 2021-12-31
1/4" Carbide Router Bit | 1 | 49.607 | tool | lee valley | 2021-12-15
5/16" Carbide Router Bit | 1 | 83.055 | tool | lee valley | 2021-12-15
5/16" Carbide Straight Plunge Router Bit | 1 | 19.662 | tool | lee valley | 2021-12-15
sand paper 600 grit | 1 | 2.147 | consumables | exotic woods burlington | 2021-12-15
sand paper 1200 grit | 1 | 2.26 | consumables | exotic woods burlington | 2021-12-15
ez mix 1/2 pint container | 1 | 0.8475 | consumables | exotic woods burlington | 2021-12-15
ez mix 1 pint container | 1 | 1.0735 | consumables | exotic woods burlington | 2021-12-15
1L ligna biosupra natural oil | 1 | 101.6435 | materials | exotic woods burlington | 2021-12-15
10' Superstrut Channel | 1 | 65.48 | materials | home depot | 2021-12-15
Mono 83ml silicone | 1 | 8.2716 | materials | home depot | 2021-12-15
Varathane 3X Triple Thick spray | 1 | 20.3061 | materials | home depot | 2021-12-15
GPS 1" insulation 4x8 | 2 | 56.4096 | materials | home depot | 2021-12-15
M8-1.25x30 bolts | 5 | 3.3561 | materials | home depot | 2021-12-28
Compost Bin | 1 | 11.2774 | household | home depot | 2021-12-28
Cutting wheel | 1 | 4.9494 | consumables | home depot | 2021-12-28
Cutting wheel | 1 | 4.5991 | consumables | home depot | 2021-12-28
1/2" 1.5" bolts | 5 | 16.7805 | materials | home depot | 2021-12-28
1/2" lock nuts | 5 | 11.978 | materials | home depot | 2021-12-28

## externalized costs
desription | category | used in | source
measuring tape | tool | all, installing flooring | pre-owned
laptop | tool | all | pre-owned
phone | tool | all | pre-owned
phone gimbal | tool | all | family
steamer | tool | removing decals | family
various scrapers | tool | removing decals | family
pressure washer | tool | detailing | family
buffing machine | tool | detailing | family
short ladder | tool | detailing | family
OBD reader | tool | vehicle maintenance | pre-owned
multimeter | tool | all | pre-owned, makerspace
socket set | tool | all | family, makerspace, bought
screwdriver set | tool | all | pre-owned, makerspace
hand drill | tool | all | girlfriend, makerspace
wire snippers | tool | electrical | pre-owned, makerspace
pliers | tool | all | pre-owned, makerspace
headlamp | tool | all | pre-owned
creeper | tool | under vehicle | family
forklift | tool | wheelchair lift removal | makerspace
paint roller | tool | painting | girlfriend
angle grinder | tool | gutting | pre-owned, makerspace
compressor | tool | removing rivets | makerspace
air chisel | tool | removing rivets | family
pry bars | tool | gutting | makerspace
mallet | tool | gutting, floor installation | makerspace
hammer | tool | all | pre-owned, makerspace
vise grips | tool | all, removing radiator | makerspace
circular saw | tool | gutting | makerspace
milling machine | tool | gridbeam | makerspace
thickness planer | tool | gridbeam | makerspace
jointer | tool | gridbeam | makerspace
table saw | tool | all, installing flooring | makerspace
clamps | tool | all | makerspace
buckets | tool | all, removing radiator | pre-owned
caulking applicator | tool | all | girlfriend, makerspace
cutter | tool | installing flooring | pre-owned, makerspace
level | tool | installing flooring | makerspace
speed square | tool | installing flooring | makerspace
mig welder | tool | !pullbar | makerspace
chop saw | tool | !pullbar | makerspace
metal grinder | tool | !pullbar | makerspace
pullbar | tool | installing flooring | built
pokey tool | tool | replacing window latches | makerspace
belt sander | tool | upgrading window latches | makerspace
bandsaw | tool | upgrading window latches | makerspace
file | tool | !pullbar, upgrading window latches | makerspace
sandpaper | tool | upgrading window latches, gridbeam | free
paintbrush | tool | upgrading window latches, painting metal surfaces | bought
T Square | tool | Cutting cork underlay, aerogel | makerspace
Engineers Square | tool | all | makerspace
Calipers | tool | all | pre-owned, makerspace
water | consumable | all | makerspace
internet | consumable | all | makerspace
electricity | consumable | all | makerspace
floodlight | tool | all | makerspace
windshield washer fluid | consumable |  | family
razor blades | consumable |  | family, makerspace
buffing pads | consumable |  | family
microfiber cloths | consumable |  | family, pre-owned
paper towel | consumable |  | family, free, makerspace
wd40 | consumable |  | family
acetone | consumable |  | family
goo gone | consumable |  | family
dawn dish soap | consumable |  | family, makerspace
plastic car trim spray | consumable |  | family
tire shine spray | consumable |  | family
green stuff organic cleaner | consumable |  | family
interior car cleaner | consumable |  | family
interior car polish | consumable |  | family
exterior car polish/wax | consumable |  | family
bar keepers friend (cleaner) | consumable |  | family
drop sheet | consumable |  | girlfriend
silicone | consumable |  | pre-owned
duct tape | consumable |  | pre-owned
shackle | material |  | family
door latch | material |  | family
fire extinguisher | material |  | family
car emergency kit | material |  | came with vehicle
wheel chonks | material |  | family, bought
windshield sun shade | material |  | family
self tapping hex head screws | material |  | came with vehicle
phone stand | tool |  | bought
foam weatherstrip | material |  | family
aluminum trim | material | installing flooring | makerspace
cab carpet | material | flooring | family
cab rubber matt | material | flooring | family
1 roll tuck tape | material |  | family
3 GE silicone tubes | material |  | family
1 cable cutter | tool |  | family

## time log
Time Log
date | descriptioon | hours
2021-07-13 | inspected 6 different buses | 6.5 | Sum of hours
2021-07-13 | picked up bus | 2.5 | 828.1087
2021-07-13 | got vehicle pre-purchase safety inspection | 0.5
2021-07-13 | got bank draft | 0.5
2021-07-13 | cleaned up trash, removed most stickers | 0.5
2021-07-13 | picked up cork underlayment | 0.5
2021-07-13 | did a bunch of research - years + months of more intense reseach
2021-07-13 | got insurance policy - took 3 weeks, then 3 days once I got angry
2021-07-14 | scouted for deals online, did research and made appointments | 5
2021-07-14 | picked up cork flooring | 2.5
2021-07-14 | bought an furnace air filter | 0.75
2021-07-14 | disconnected bus door exterior emergency latch | 0.5
2021-07-14 | removed all wheelchair straps, seatbelts and storage pouches | 0.5
2021-07-14 | installed rear door lock | 0.2
2021-07-15 | picked up bottle jack fan, respirator | 3
2021-07-15 | got new tires installed | 1
2021-07-15 | took measurements of the bus cleaned a window | 0.5
2021-07-15 | bought and installed new wipers | 0.5
2021-07-16 | got safety inspection certificated | 2.75
2021-07-16 | removed stickers | 1
2021-07-16 | cleaned windows and mirrors | 1
2021-07-16 | rebalanced front tires | 0.5
2021-07-16 | removed Zonar inspection system tags | 0.25
2021-07-16 | vaccummed | 0.25
2021-07-16 | disabled rear door lock alarm | 0.25
2021-07-16 | tested actual consumption of box fan | 0.15
2021-07-16 | threw out garbage | 0.15
2021-07-16 | removed cable tie downs | 0.15
2021-07-16 | zip-tied accessibility door handle to wheelchair lift | 0.15
2021-07-17 | removed stickers and decals | 2
2021-07-17 | road force balanced rear tires | 1.5
2021-07-17 | cleaned dashboard | 0.5
2021-07-17 | cleaned cab floor | 0.5
2021-07-17 | cleaned cab door | 0.5
2021-07-17 | removed rusty fire extinguisher holder | 0.25
2021-07-18 | removed decals | 10
2021-07-18 | cleaned and detailed | 10
2021-07-18 | added lock to the rear side door | 0.5
2021-07-19 | finished registration, got license plate sticker | 1
2021-07-20 | project management and documentation | 2
2021-08-11 | organized stuff inside | 2
2021-08-11 | added weather stripping to windows | 1
2021-08-11 | cleaned glue off back of bus | 0.5
2021-08-12 | cleaned outside and glue | 0.75
2021-08-12 | removed stairs flooring | 0.5
2021-08-12 | cleaned | 0.5
2021-08-20 | removed center ceiling, partial | 1.25
2021-08-20 | removed passanger side wall, insulation | 1
2021-08-20 | removed passanger side divider | 1
2021-08-20 | removed ceiling rivets | 1
2021-08-20 | cleaned | 0.5
2021-08-20 | removed left/right wiring conduits | 0.25
2021-08-21 | moved everything (flooring, underlayment, insulation, junk, etc) out of the bus and into my home | 4
2021-08-22 | went to princess auto to buy stuff | 4
2021-08-23 | removed tape from underlayment | 4
2021-08-23 | planning | 2
2021-08-27 | removed driver side divider | 2
2021-08-27 | removed chair | 2
2021-08-27 | removed rivets | 1
2021-08-27 | cleaned | 0.5
2021-08-28 | removed ceiling | 5
2021-08-28 | removed driver side wall and insulation | 3
2021-08-28 | removed chair | 2
2021-08-28 | removed rear wall and insulation | 1
2021-08-28 | scraped insulation off ceiling | 0.5
2021-08-28 | cleaned | 0.5
2021-08-28 | planning | 0.5
2021-08-28 | snipped wire conduit holes | 0.25
2021-08-28 | removed screws in flooring | 0.25
2021-08-28 | removed wheelchair lift 2 bolts | 0.25
2021-08-29 | removed Q'straint pucks (15/32) | 2.5
2021-08-29 | removed linoleum floor | 1
2021-08-29 | removed plywood from front of bus and cleaned up large rust | 0.5
2021-08-29 | removed rivets and insulation from wire conduit | 0.5
2021-08-29 | cleaning | 0.5
2021-08-29 | read instructions for respirator and filters | 0.25
2021-08-29 | removed rear door overhead plastic | 0.25
2021-08-30 | removed Q'straint pucks (14/32) | 4
2021-08-30 | removed rust and goo around plywood | 0.5
2021-08-30 | documentation | 0.33
2021-08-30 | removed 1/4 of plywood front-passanger side | 0.25
2021-08-30 | removed removed bolts and screws | 0.25
2021-08-31 | removed and sold lift | 2
2021-08-31 | removed plywood | 1.5
2021-08-31 | removed Q'straint pucks (3/32) | 1
2021-08-31 | sorted garbage | 1
2021-08-31 | documentation | 0.333
2021-09-01 | removed cables running under bus from wheelchair lift | 1.5
2021-09-01 | packed garbage in the bus | 1
2021-09-01 | removed remaining plywood | 0.5
2021-09-01 | removed metal wall panels | 0.5
2021-09-01 | removed cable conduits | 0.5
2021-09-02 | took garbage to eco centre, weighed it and threw it out | 3
2021-09-02 | went shopping for materials, tools | 0.5
2021-09-03 | went shopping for materials, tools | 0.5
2021-09-03 | tallied up garbage weights | 0.15
2021-09-06 | cleaned up rust, glue, paint | 6
2021-09-06 | planning and research | 2
2021-09-06 | documentation | 0.2
2021-09-07 | cleaned up rust, glue, paint | 3
2021-09-07 | did some research | 3
2021-09-07 | pulled out bulkhead panels, plastic, etc | 2
2021-09-07 | cleaned fiberglass bits off the walls | 1
2021-09-08 | did some research and purchases | 3
2021-09-09 | did some research and made purchases | 9
2021-09-09 | documentation | 1
2021-09-12 | CAD and design | 2
2021-09-13 | cleaned up the wiring | 4
2021-09-13 | CAD and design | 3
2021-09-13 | stripped paint and gunk | 2
2021-09-14 | CAD and design | 3
2021-09-15 | cleaned up the wiring | 4
2021-09-22 | stripped floor, doors and cleaned | 9
2021-09-22 | cleaned up wiring | 0.5
2021-09-23 | stripped the floor and door | 4
2021-09-27 | stripped the floor | 4
2021-09-27 | prepared bus and materials for stripping and painting | 1.5
2021-09-28 | stripped the floor | 6
2021-09-28 | cleaned for painting | 1
2021-09-28 | painted floor | 1
2021-09-28 | removed radiator | 0.75
2021-09-28 | removed seats | 0.25
2021-09-29 | second coat of paint | 0.5
2021-09-29 | cleaned radiator | 0.25
2021-09-29 | finished registration, got license plate sticker | 0.25
2021-10-01 | designing utilities/bed | 2
2021-10-01 | moved stuff out of my room | 2
2021-10-01 | ordered crimper | 0.5
2021-10-01 | picked up packages | 0.5
2021-10-02 | traded stuff on bunz | 3
2021-10-02 | organized the space | 1
2021-10-02 | took inventory of pantry | 1
2021-10-02 | made wishlist for pantry | 1
2021-10-02 | investigated pantry container options | 0.5
2021-10-03 | assembled and tested diesel heater | 4
2021-10-03 | organized todos | 1
2021-10-03 | brought inside materials from the bus | 0.5
2021-10-03 | logged hours | 0.25
2021-10-04 | researched furniture construction, woodworking and gridbeam method | 8
2021-10-04 | removed rivets and glue | 5
2021-10-04 | deep clean | 3
2021-10-04 | designed interior space, organized tasks and systems level architecture | 3
2021-10-04 | painted with corroseal | 2
2021-10-04 | removed drivers seat | 1
2021-10-05 | second coat of corroseal | 2
2021-10-05 | research | 2
2021-10-05 | sorted and went through hardware | 1
2021-10-05 | looked into gridbeam some more | 1
2021-10-05 | unloaded wood from the bus | 0.25
2021-10-06 | making aluminum short gridBeam jig, doing tests | 5
2021-10-06 | picking up supplies | 4
2021-10-06 | setup and tear down | 3
2021-10-06 | painted first coat of black paint | 1.5
2021-10-06 | prepped surface for painting | 1
2021-10-06 | bought painting supplies | 0.5
2021-10-07 | prepped and painted second coat in the front area | 3
2021-10-07 | online shopping | 3
2021-10-07 | planning | 2
2021-10-07 | cleaned chairs, floor and door seals | 0.5
2021-10-08 | installed cork underlay | 4
2021-10-08 | making 8ft aluminum L bar gridbeam jig | 3.5
2021-10-08 | shopping for lumber, picking up orders | 3
2021-10-08 | making gridbeam | 3
2021-10-08 | learning about wood and finishes | 2
2021-10-08 | caulked main door window back into place | 1
2021-10-08 | stripped drivers chair of rust and chipped paint | 0.5
2021-10-09 | making gridbeam | 10
2021-10-09 | project planning, organization | 4
2021-10-10 | making gridbeam | 10
2021-10-11 | making gridbeam | 10
2021-10-12 | installed flooring | 6
2021-10-12 | taped up passenger seat holes | 0.25
2021-10-14 | made some super precise gridbeam for a jig idea | 3
2021-10-14 | planed the remaining wood | 1.5
2021-10-14 | cut raw lumber into blanks | 1
2021-10-14 | calculated allowable tolerance based on ideal and real bolt and hole sizes | 0.5
2021-10-15 | removed flooring and relayed underlayment | 6
2021-10-15 | took an inventory of all the wood | 1.5
2021-10-15 | explored option to build BeamCNC, collected parts | 1
2021-10-15 | measured out all cuts on raw lumber | 1
2021-10-15 | organized bus | 1
2021-10-15 | prototyped bed structure | 0.5
2021-10-15 | mock install of insulation, window dressing | 0.5
2021-10-15 | thought about electrical layout | 0.25
2021-10-16 | data entry and organization | 2
2021-10-17 | project planning, organization | 4
2021-10-18 | installed and leveled flooring | 7
2021-10-19 | did a lot of research on electrical systems, propane, found a battery | 8
2021-10-19 | project planning, organization | 4
2021-10-20 | purchased battery | 3
2021-10-20 | replaced and reinforced window latches | 2
2021-10-20 | moved stuff into studio | 2
2021-10-20 | researched propane | 2
2021-10-20 | project planning | 1
2021-10-20 | purchased mr buddy heater | 0.5
2021-10-21 | project planning | 10
2021-10-21 | researched propane | 2
2021-10-21 | purchased electrical components | 2
2021-10-22 | researched, designed and purchased for Electrical, HVAC, Sensors | 14
2021-10-23 | researched, designed and purchased for Electrical, HVAC, Sensors | 14
2021-10-24 | researched, designed and purchased for Electrical, HVAC, Sensors | 12
2021-10-25 | picked up solar panels | 3
2021-10-25 | researched where to weigh bus | 1
2021-10-25 | picked up stuff from Vivs closet | 0.5
2021-10-25 | tested LED remote and lights | 0.25
2021-10-25 | sanded and painted window latches | 0.2
2021-10-25 | tested DeWalt Drill + Driver | 0.1
2021-10-26 | researched and made purchases for electrical | 8
2021-10-26 | read manual for Inverter/Charger | 3
2021-10-26 | smashed and cleaned window | 2
2021-10-27 | researched electrical and made schematic | 4
2021-10-27 | unloaded bus | 0.5
2021-10-27 | installed latches | 0.25
2021-10-27 | cleaned limescale off window | 0.25
2021-10-28 | designing utilities/bed | 6
2021-10-28 | finished schematic | 2
2021-10-28 | picked up free cable | 1
2021-10-29 | designing utilities/bed | 4
2021-10-29 | tared bus | 3
2021-10-29 | picked up 4/0 AWG cable and lugs | 0.75
2021-10-29 | measured undercarriage | 0.75
2021-10-29 | made a weight log | 0.5
2021-10-29 | research fuel tank aux line | 0.25
2021-10-29 | research passanger seat | 0.25
2021-10-30 | designing utilities/bed | 4
2021-10-30 | moved stuff from my apartment and into makerspace | 2
2021-10-30 | made a pile of stuff to give away | 2
2021-10-30 | covered bus windows with garbage bags | 2
2021-10-31 | organized the studio space, parts and components | 6
2021-10-31 | designing utilities/bed | 2
2021-10-31 | put out stuff for people to take | 2
2021-10-31 | cut bus bars | 1
2021-10-31 | took out garbage | 0.5
2021-11-22 | installed insulation | 6.5
2021-11-22 | upgraded logs to excel, maintained and updated with new data | 3
2021-11-24 | removed unecessary wiring | 0.5
2021-11-25 | cut and sanded aluminum floor trim | 2
2021-11-25 | cut wood to rough gridbeam blanks | 1.5
2021-11-25 | cut insulation to size | 0.3
2021-11-26 | bought supplies | 4
2021-11-26 | cleaned and organized | 3
2021-11-27 | bought sewing supplies, washed fabric | 2
2021-11-28 | drilled hole in anchor rail, tried out installation | 2.15
2021-11-28 | cut 5ft x 8 gridbeam blanks | 2
2021-11-28 | added in costs to log | 0.93333
2021-11-28 | organized tasks | 0.75
2021-11-28 | moved stuff from bus to workshop, cleaned up, wrapped up mattress | 0.5
2021-11-28 | inspected seals on body | 0.5
2021-11-28 | taped up floor layout for heater | 0.33
2021-11-29 | cut gridbeam blanks | 2.8167
2021-11-29 | sorted and threw out trash | 1.066
2021-11-30 | cut, taped and installed insulation | 2.75
2021-11-30 | cut blanks to length and QC for straightness | 1.92
2021-11-30 | sanded 2ft pieces | 0.5
2021-12-01 | cut, taped and installed insulation | 2
2021-12-01 | unknown | 2
2021-12-01 | cleanup and garbage weighing | 1.5
2021-12-02 | cut, taped and installed insulation | 2.75
2021-12-02 | contacrted metal laser cutters for a quote | 0.333
2021-12-02 | went shopping for supplies | 0.33
2021-12-04 | changed oil, oil filter, drained fuel water separator, cleaned mass airflow sensor | 6
2021-12-05 | moved stuff out of lespacemaker, drove to parents house | 14
2021-12-06 | move stuff in, settled into new work space | 6
2021-12-06 | requested quotes for gridbeam steel parts | 2
2021-12-06 | setup 3d print for gridbeam | 2
2021-12-07 | cut and installed insulation | 8
2021-12-07 | made orders for supplies | 2
2021-12-07 | went through gridbeam BOM to think through possible issues | 2
2021-12-07 | organized tasks | 1
2021-12-07 | cleaned and oiled up rusty anchor plates | 1
2021-12-07 | got quotes for steel L bar and waterjet cut for gridbeam template | 0.2
2021-12-08 | cut and installed insulation | 6
2021-12-08 | CNC machine | 5
2021-12-08 | organization | 2
2021-12-08 | Shopping | 1.5
2021-12-08 | sanded aluminum pieces | 1
2021-12-08 | aerogel sewing attempt by professionals | 1
2021-12-08 | aerogel sewing attempt | 0.5
2021-12-09 | finished interior wall insulation job | 3
2021-12-09 | picked up seat from junkyard | 3
2021-12-09 | CNC machine - tested electronics, 3d prints | 2
2021-12-09 | picked up and delivered metal to waterjet cutters | 1.5
2021-12-09 | cleaned seat | 1
2021-12-09 | picked up some tape | 0.2
2021-12-10 | insulated ceiling | 7
2021-12-10 | picked up waterjet pieces | 1.25
2021-12-10 | went to talk to pros about gluing/sewing aerogel | 1
2021-12-10 | organization | 1
2021-12-10 | CNC | 8
2021-12-11 | CNC | 10
2021-12-11 | Seal Exterior Envelope | 3
2021-12-11 | changed fuel filters, added diesel kleen, "fixed" hazard lights, cut lumber for lifting bus | 2.5
2021-12-11 | organization | 1
2021-12-12 | CNC | 8
2021-12-12 | closing in rear wall with angle | 5
2021-12-12 | Seal Exterior Envelope | 3
2021-12-12 | Sewing/sealing window covers | 3
2021-12-12 | went shopping for supplies | 2
2021-12-12 | organization | 2
2021-12-12 | Sanded 5 plywood boards for oiling | 1.5
2021-12-12 | checked seat mounting options | 0.5
2021-12-12 | mineral deposit window cleaning attempt | 0.5
2021-12-13 | CNC | 0.5
2021-12-13 | logs | 1
2021-12-14 | oiled wood
2021-12-14 | wrote gcode, setup endstops, tested (cnc)
2021-12-14 | cleaned up wiring in the back or the bus
2021-12-14 | cleaned window
2021-12-14 | aerogel edges
2021-12-14 | framed rear of bus
2021-12-14 | cleaning and organization
2021-12-15 | organization
2021-12-15 | shopping
2021-12-15 | CNC
2021-12-15 | insulation framing
2021-12-16 | cleanup and garbage weighing | 0.16667
2021-12-16 | closing back wall | 6.5
2021-12-16 | sanding wood | 1.5
2021-12-16 | oiling wood | 0.5
2021-12-16 | aerogel | 2
2021-12-16 | insulation retaining bars | 4
2021-12-16 | cnc | 0.33333
2021-12-16 | cleanup | 0.16667
2021-12-17 | building bedframe | 14
2021-12-17 | cnc | 1
2021-12-17 | aerogel | 1
2021-12-17 | insulation framing | 3
2021-12-17 | rear wall framing | 2
2021-12-18 | sanding wood | 2
2021-12-18 | aerogel | 2
2021-12-18 | mounting solar panels (2 people) | 13
2021-12-19 | finished insulation framing | 3
2021-12-19 | sanding and oiling wood | 6
2021-12-19 | clean up | 1
2021-12-20 | packing for trip | 8
2021-12-20 | rear wall | 4
2021-12-20 | oiling wood | 4
2021-12-21 | packing for trip | 3
2021-12-21 | oiled wood | 2
2021-12-22 | rear wall | 2
2021-12-23 | rear wall | 2
2021-12-23 | electrical | 2
2021-12-24 | bed install, cutting wood | 8
2021-12-25 | electrical, furniture, rear wall, cleanup | 16
2021-12-26 | clean up | 2
2021-12-26 | heater install | 3
2021-12-26 | rear wall | 1
2021-12-26 | other shit | 3
2021-12-27 | heater install | 9
2021-12-28 | installed chair | 3
2021-12-29 | electrical (wired up distribution panel, DCDC charger) | 4
2021-12-28 | installed electrical (wired up bus bars) | 3
2021-12-27 | velcro / aerogel | 1
2021-12-28 | velcro / aerogel | 1
2021-12-28 | cut window sills | 3
2021-12-28 | go to home depot to pick up supplies | 1
2021-12-28 | packing for trip | 3
2022-01-01 | researched and bought new batteries | 2
2022-01-20 | fixed hanging coolant line, replaced turn signal bulb, cleaned windows/mirrors, inspected fluids | 1.75
2022-01-20 | cleaned bus | 0.5
2022-01-20 | installed insulation | 0.5
2022-02-05 | installed insulation | 1
2022-03-01 | fixed bent rear bumper | 2
2022-03-01 | siliconed velcro | 0.5
2022-03-01 | wiring solar | 2
2022-03-01 | wiring inverter | 2
2022-03-01 | reorganizing bus | 4
2022-03-01 | buying stuff | 2
2022-03-01 | setting up remote controlled door | 1
2022-03-01 | programming inverter and setting up bluetooth dongle | 1
2022-03-01 | mounting camera | 1
2022-03-01 | shopping | 1
2022-03-01 | wiring up router and 12v socket | 1
2022-03-01 | setting up OpenWRT and Security camera | 2
2022-03-01 | designing software and smart systems | 3
2022-03-01 | setting up OpenWRT WWLAN | 1
2022-03-01 | setting up OpenWRT FTP Server | 6
2022-03-09 | wiring up solar system | 2
2022-03-10 | wired venusOS Raspberry Pi | 1
2022-03-10 | setup LED lights | 2

## water log
date | quantity (L)
2022-01-01 | 10
2022-02-01 | 12.5
2022-02-01 | 4.7
2022-02-01 | 15.2
2022-02-01 | 19.2
2022-03-01 | 19.7
2022-03-11 | 10.2

## gas log
[8 empty] | L/100km | (Multiple Items)
# | date | location | cost | liters | km | L/100km | $/L
1 |  |  | 150.6 | 121.6 | 613.2 | 19.8304 | 1.2385 | Values
2 | 2021-07-19 | Montreal, QC | 150 | 117.28 | 510.7 | 22.9646 | 1.279 | # of Fillups | 7
3 | 2021-08-24 | Ingleside, ON | 146.77 | 112.6 | 557.3 | 20.2046 | 1.3035 | Total Fuel | 866.925
4 | 2021-09-15 | Montreal, QC | 152.51 | 117.4 | 593.2 | 19.791 | 1.2991 | Total Mileage | 4202.8
5 | 2021-09-17 | Cobourg, ON | 159.6 | 123.8 | 736.1 | 16.8184 | 1.2892 | Total Cost | 1175.38
6 | 2021-09-21 | Montreal, QC | 150 | 117.279 | 689 | 17.0216 | 1.279 | Non-Weighted Average Cost per Litre | 1.3501
7 | 2021-10-20 | Montreal, QC | 180.56 | 123.8 |  | #DIV/0! | 1.4585 | Average Mileage | 20.8408
8 | 2021-12-09 | Mississauga, ON | 168.83 | 121.545 | 604 | 20.1233 | 1.389
9 | 2021-12-29 | Sudbury, ON | 173.24 | 130 | 535 | 24.2991 | 1.3326
10 | 2021-12-30 | Wawa, ON | 150 | 101.419 | 565 | 17.9503 | 1.479
11 | 2021-12-31 | Lac Des Mill, ON | 223.83 | 139.98 | 564 | 24.8191 | 1.599
12 | 2022-01-01 | Steinbach, MB | 173.41 | 124.842 | 381.4 | 32.7326 | 1.389
13 | 2022-01-01 | Moosomin, SK | 174.73 | 127.632 | 468.1 | 27.266 | 1.369
14 | 2022-01-02 | Swift Current, SK | 169.3 | 118.472 | 541.5 | 21.8785 | 1.429
15 | 2022-01-03 | Calgary, AB | 167.06 | 122.033 | 471.2 | 25.8983 | 1.369
16 | 2022-01-08 | Revelstoke, BC | 165.78 | 104.991 | 520 | 20.1906 | 1.579
17 |  |  |  |  | 570 | 0 | #DIV/0!
18 |  |  |  |  | 453 | 0 | #DIV/0!
19 |  |  |  |  | 421.1 | 0 | #DIV/0!
20 | [5 empty] | #DIV/0! | #DIV/0!

## maintenance log
Date | Mileage | Action
2021-07-12 | 175490 | changed wipers
2021-07-12 | 175490 | changed tires
2021-07-12 | 175490 | tires road force balanced
2021-12-20 | 179966 | changed engine oil and filter
2021-12-20 | 179966 | cleaned MAF (mass airflow sensor)
2021-12-20 | 179966 | changed fuel filters
2022-01-20 | 185694 | replaced front right turn signal bulb
2022-01-20 | 185694 | replaced FOH, heated mirror fuses
2022-01-20 | 185694 | retorqued wheel lugs
2022-01-20 | 185694 | set tire pressure to weight spec
2022-01-20 | 185694 | changed front right wheel hub
2022-02-22 | 189132 | changed engine oil and filter
2022-02-22 | 189132 | changed air filter